Project Planning Phase

Project Planning - Product Backlog, Sprint Planning, Stories, Story Points

| Date | 05 September 2026 |
| --- | --- |
| Team ID | ServiceNow |
| Project Name | Medical Diagnosis Center Service Portal |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the backlog below to represent the planned work for the Medical Diagnosis Center Service Portal.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Service Portal & Patient Setup | US-1 | As a patient, I can access the Medical Diagnosis Center Service Portal and view the available services. | 2 | High | ServiceNow Team |
| Sprint-1 |  | US-2 | As a patient, I can provide my details so that a patient record can be created for my diagnostic request. | 2 | High | ServiceNow Team |
| Sprint-1 | Diagnostic Test Management | US-3 | As a patient, I can view available diagnostic tests and their details before booking. | 2 | High | ServiceNow Team |
| Sprint-1 |  | US-4 | As an administrator, I can create and maintain diagnostic test records and fields. | 3 | High | ServiceNow Team |
| Sprint-1 | Appointment Booking | US-5 | As a patient, I can select a diagnostic test, date and available time slot and submit a booking. | 3 | High | ServiceNow Team |
| Sprint-1 |  | US-6 | As a patient, I can enter mandatory details and receive validation when booking information is incomplete or invalid. | 3 | High | ServiceNow Team |
| Sprint-2 | Appointment Workflow | US-7 | As a lab/admin user, I can manage appointment approval and lifecycle status through an automated workflow. | 5 | High | ServiceNow Team |
| Sprint-2 | Notifications | US-8 | As a patient, I can receive booking or approval confirmation notifications. | 2 | High | ServiceNow Team |
| Sprint-2 |  | US-9 | As a patient, I can receive a notification when my diagnostic report becomes available. | 2 | High | ServiceNow Team |
| Sprint-2 | Payments | US-10 | As a patient, I can view and track the payment status of my diagnostic service. | 3 | High | ServiceNow Team |
| Sprint-2 | Reports | US-11 | As a lab user, I can create and maintain the diagnostic report for a completed appointment. | 3 | High | ServiceNow Team |
| Sprint-2 |  | US-12 | As a patient, I can view or download my available diagnostic report from the portal. | 2 | High | ServiceNow Team |
| Sprint-2 | Security & Monitoring | US-13 | As an administrator, I can control access to application data using roles and ACLs. | 3 | High | ServiceNow Team |
| Sprint-2 |  | US-14 | As an administrator, I can view dashboard information for monitoring diagnostic center operations. | 2 | Medium | ServiceNow Team |

Project Planning Phase

Project Tracker, Velocity & Burndown Chart

Project Tracker (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 15 | 6 Days | 07 Sep 2026 | 12 Sep 2026 | 15 | 12 Sep 2026 |
| Sprint-2 | 22 | 6 Days | 14 Sep 2026 | 19 Sep 2026 | 22 | 19 Sep 2026 |

Velocity:

Total Story Points = 15 + 22 = 37

Number of Sprints = 2

Average Velocity = Total Story Points Completed / Number of Sprints

Average Velocity = 37 / 2 = 18.5 Story Points per Sprint

Burndown Chart:

The planned burndown below shows the expected reduction of remaining story points across the two sprints.

| Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Remaining points - Sprint 1 | 15 | 13 | 10 | 8 | 5 | 2 | 0 |
| Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 |
| Remaining points - Sprint 2 | 22 | 19 | 16 | 12 | 9 | 5 | 0 |
| Combined Remaining | 37 | 32 | 26 | 20 | 14 | 7 | 0 |
| Note | Sprint 1 |  |  |  |  |  | Sprint 2 |
| Planned trend | Start |  |  |  |  |  | Complete |
| Basis | Story points planned for the project |  |  |  |  |  |  |

Planned Burndown Interpretation: The remaining work decreases as stories are completed. The chart is a planned project view; actual burn-down can be updated at the end of each sprint.

Project Planning Phase

Burndown Chart

A burndown chart is a graphical representation of work left to do versus time. It is commonly used in Agile / Scrum planning.

Planned Medical Diagnosis Center Burndown

| Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ideal remaining | 37 | 32 | 27 | 22 | 17 | 12 | 6 | 0 |
| Sprint 1 end |  |  |  |  |  |  | 15 |  |
| Sprint 2 end |  |  |  |  |  |  |  | 0 |
| Planned remaining | 37 | 32 | 26 | 20 | 14 | 7 | 0 |  |
| Sprint-1 | 07-12 Sep 2026 | 15 points |  |  |  |  |  |  |
| Sprint-2 | 14-19 Sep 2026 | 22 points |  |  |  |  |  |  |

Planning Assumptions:

• The backlog and story points are planning estimates for the Medical Diagnosis Center Service Portal.

• Two 6-day sprints are used to match the trainer's example structure.

• Team Members are shown as 'ServiceNow Team' because individual member names were not provided.

• Sprint release dates are planned dates for documentation; they should be replaced with actual dates if the project schedule differs.